## Slide 1
PERTH, LAGS, CRASHING & Resource SCheduling
METODA KUANTITATIF
Magister Manajemen
Universitas Komputer Indonesia
Source:
Larson, e.w., Gray C.F., 2011, 5tH ed.;
Pinto, j.k. 2010, 2ND. ED.

## Slide 2: PROJECT PLANNING
1. Network Planning :
  Critical Path Method (CPM)
  Program/Project Evaluation and Review Technique (PERT)
  Precedence Diagram Method (PDM)
2. Project Crashing

## Slide 3: PERT (PROGRAM EVALUATION & REVIEW TECNIQUE)
In 1958 the Special Office of the Navy and the Booze Allen, and Hamilton consulting firm developed PERT to schedule the more than 3,300 contractors of the Polaris submarine project and to cover uncertainty of activity time estimates.
PERT is almost identical to the critical path method (CPM) except it assumes each activity duration has a range that follows a statistical distribution.

## Slide 4: Activity and Project Frequency Distributions
Activity
Project
m
a
b
TE

## Slide 5: Weighted Average Activity (te)
        a + 4m + b
te = -------------
6
te = weighted average activity time
a = optimistic activity time (1 chance in 100 compliting activity under normal conditions)
b = pesimistic activity time
m = most likely activity time

## Slide 6: Activity Standard Deviation
  b - a
  σte = -----
  6
  σTE = √ ∑ (σte )²

## Slide 7: Probability of Completing the Project in Time
Ts – TE
Z = --------------
√ ∑ (σte )²
TE = Critical path duration
TS = Schedule project duration
Z = probability (of meeting scheduled duration) found in statistical

## Slide 8: Z Values and Probabilities
Z Value | Probability | Z Value | Probability
-3.0 | .001 | +0.0 | .500
-2.8 | .003 | +0.2 | .579
-2.6 | .005 | +0.4 | .655
-2.4 | .008 | +0.6 | .726
-2.2 | .014 | +0.8 | .788
-2.0 | .023 | +1.0 | .841
-1.8 | .036 | +1.2 | .885
-1.6 | .055 | +1.4 | .919
-1.4 | .081 | +1.6 | .945
-1.2 | .115 | +1.8 | .964
-1.0 | .159 | +2.0 | .977
-0.8 | .212 | +2.2 | .986
-0.6 | .274 | +2.4 | .992
-0.4 | .345 | +2.6 | .995
-0.2 | .421 | +2.8 | .997

## Slide 9: Example
Activity | a | m | b
1-2 | 17 | 29 | 47
2-3 | 6 | 12 | 24
2-4 | 16 | 19 | 28
3-5 | 13 | 16 | 19
4-5 | 2 | 5 | 14
5-6 | 2 | 5 | 8
1. Compute the expected time for each activity
2. Compute the variance for each activity
3. Compute the expected project duration
4. What is the probability of completing the project by day 67?
Within 60 days?

## Slide 10: ANSWER

## Slide 11: Answer – Hypothetical Network
0 | A | 
 | 30 | 
ES | ID | EF
SL | Description | 
LS | Dur | LF
 | B | 
 | 13 | 
 | C | 
 | 20 | 
 | D | 
 | 16 | 
 | F | 
 | 5 | 
Legend
 | E | 
 | 6 | 

## Slide 12: Answer - Probability
Ts – TE
Z = --------------
√ ∑ (σte )²
        67 – 64 + 3
Z = ----------------- = -------- = + 0.5
√ 25 + 9 + 1 + 1 √ 36
P = 0.69

## Slide 13: Exercise 1
Given the project information below, what is the probability of completing the National Holiday Toy project in 93 time units?
Act. ID | Description | Predecessor | Optm.(a) | Most Likely (m) | Pess (b)
1 | Design package | None | 6 | 12 | 24
2 | Design product | 1 | 16 | 19 | 28
3 | Build package | 1 | 4 | 7 | 10
4 | Secure patent | 2 | 21 | 30 | 39
5 | Build product | 2 | 17 | 29 | 47
6 | Paint | 3,4,5 | 4 | 7 | 10
7 | Test market | 6 | 13 | 16 | 19

## Slide 14: LAGS IN PRECEDENCE RELATIONSHIP
The term Lag refer to the logical relationship between the start and finish of another. In practice, lags are sometimes incorporated into networks to allow for greater flexibility in network construction.
The commonly lags occur under four logical relationships between tasks:
1. Finish to start
2. Finish to finish
3. Start to start
4. Start to finish

## Slide 15
CRASHING PROJECTS

## Slide 16: CRASHING PROJECT
At times it is necessary to expedite the project, to accelerate development to reach an earlier completion date. The process of accelerating a project is referred to as crashing. Crashing a project directly relates to resource commitment. The more resources we are willing to expend, the faster we can push the project to its finish.

## Slide 17: Reasons to Crash a Project
The initial schedule may be to optimistic.
Market needs change and the project is in demand earlier than anticipated.
The project has slipped considerably behind schedule.
The contractual situation provides even more incentive to avoid schedule slippage.

## Slide 18: Options for Accelerating Activities
Improving the productivity of existing project resources.
Changing the working method employed for the activity, usually by altering the technology and types of resources employed.
Increasing the quantity of project resources, including personnel, plant, and equipment.

## Slide 19: Time-Cost Trade-Offs for Crashing Activities
Crashed
Normal
Cost
Crashed
Normal
Time
Crashed Point
Normal Point

## Slide 20: COST OF CRASHING
        Crash Cost – Normal Cost
Slope = ------------------------
        Normal Time – Crash Time

## Slide 21: EXAMPLE
Calculate the cost of crashing project activities, suppose the normal activity duration of activity X is 5 weeks and is budgeted cost $12,000. The crash time for this activity is 3 weeks and is expected to cost $32,000.

## Slide 22: Project Activities & Costs (Example)
Activity | Normal Duration Cost |  | Crash Duration Cost | 
A | 5 days | $ 1,000 | 3 days | $ 1,500
B | 7 days | 700 | 6 days | 1,000
C | 3 days | 2,500 | 2 days | 4,000
D | 5 days | 1,500 | 5 days | 1,500
E | 9 days | 3,750 | 6 days | 9,000
F | 4 days | 1,600 | 3 days | 2,500
G | 6 days | 2,400 | 4 days | 3,000
H | 8 days | 9,000 | 5 days | 15,000
TOTAL COST= |  | 22,450 |  | $ 37,500

## Slide 23: Cost of Crashing Each Activity
Activity | Crashing Cost (per day)
A | $ 250
B | 300
C | 1,500
D | 0
E | 1,750
F | 900
G | 300
H | 2,000

## Slide 24: Normal Activity Network
A
5
E
9
C
3
B
7
D
5
G
6
H
8
F
4

## Slide 25: Fully Crashed Activity Network
A
3
E
6
C
2
B
6
D
5
G
4
H
5
F
3

## Slide 26: EXERCISE -2
You are considering the decission of whether or not to crash your project. After asking your operation manager to conduct an analysis, you have determined the crash activity duration and costs, shown in the table below (assume all activities are on the critical path):
Activity | Normal Duration Cost |  | Crashed Duration Cost | 
A | 6 days | $ 1,000 | 4 days | $ 2,000
B | 5 days | $ 2,500 | 5 days | $ 2,500
C | 3 days | $ 800 | 2 days | $ 1,200
D | 7 days | $ 3,500 | 3 days | $ 7,000
E | 2 days | $ 500 | 1 day | $ 5,000
F | 5 days | $ 2,000 | 4 days | $ 3,000
G | 10 days | $ 5,000 | 6 days | $ 6,300
a. Calculate the per day cost for crashing each activity
b. Which are the most attractives candidates for crashing? Why?

## Slide 27: EXERCISE -3
Given the data and information that follow, compute the total direct cost for each duration. If the indirect costs for each project duration are $90 (15 time units), $70 (14), $50 (13), $40 (12), and $30 (11), compute the total project cost for each duration. What is the optimum cost-time schedule for the project? What is this cost?
Act. | Crash cost (slope) | Maximum crash time | Normal time | Normal cost
A | 20 | 1 | 5 | 50
B | 60 | 2 | 3 | 60
C | 0 | 0 | 4 | 70
D | 10 | 1 | 2 | 50
E | 60 | 3 | 5 | 100
F | 100 | 1 | 2 | 90
G | 30 | 1 | 5 | 50
H | 40 | 0 | 2 | 60
I | 200 | 1 | 3 | 200

## Slide 28: Exercise 3 - Network Model
A
5
C
D
F
G
I
B
E
H

## Slide 29
RESOURCE SCHEDULING

## Slide 30: Types of Resource Constraint
1. People
2. Material
3. Equipment

## Slide 31: Resource- Constrained Schedule Sample
0 | 1 | 2
0 | 2P | 0
0 | 2 | 2
ES | ID | EF
SL | RES | SL
LS | Dur | LF
2 | 2 | 8
2 | 2P | 2
4 | 6 | 10
2 | 3 | 6
0 | 2P | 0
2 | 4 | 6
6 | 5 | 8
2 | 1P | 2
8 | 2 | 10
10 | 7 | 12
0 | 1P | 0
10 | 2 | 12
Legend
6 | 6 | 10
0 | 1P | 0
6 | 4 | 10
2 | 4 | 4
6 | 1P | 6
8 | 2 | 10

## Slide 32: ES RESOURCE LOAD CHART
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 2P | 2 | 0 | 2 | 0 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 2P | 6 | 2 | 10 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  | 
3 | 2P | 4 | 2 | 6 | 0 |  |  | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
4 | 1P | 2 | 2 | 10 | 6 |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
5 | 1P | 2 | 6 | 10 | 2 |  |  |  |  |  |  | 1 | 1 |  |  |  |  |  |  | 
6 | 1P | 4 | 6 | 10 | 0 |  |  |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 
7 | 1P | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 
Total resource load |  |  |  |  |  | 2P | 2P | 5P | 5P | 4P | 4P | 4P | 4P | 1P | 1P | 1P | 1P |  |  | 

## Slide 33: RESOURCE CONSTRAIN SCHEDULE
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 2P | 2 | 0 | 2 | 0 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 2P | 6 | 2 | 10 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  | 
3 | 2P | 4 | 2 | 6 | 0 |  |  | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
4 | 1P | 2 | 2 | 10 | 6 |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
5 | 1P | 2 | 6 | 10 | 2 |  |  |  |  |  |  | 1 | 1 |  |  |  |  |  |  | 
6 | 1P | 4 | 6 | 10 | 0 |  |  |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 
7 | 1P | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 
Total resource load |  |  |  |  |  | 2P | 2P | 5P | 5P | 4P | 4P | 4P | 4P | 1P | 1P | 1P | 1P |  |  | 
Resource available |  |  |  |  |  | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 

## Slide 34: RESOURCE CONSTRAIN SCHEDULE
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 2P | 2 | 0 | 2 | 0 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 2P | 6 | 6 | 12 | 0 |  |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 
3 | 2P | 4 | 2 | 6 | 0 |  |  | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
4 | 1P | 2 | 2 | 10 | 6 |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
5 | 1P | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 
6 | 1P | 4 | 6 | 10 | 0 |  |  |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 
7 | 1P | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 | 
Total resource load |  |  |  |  |  | 2P | 2P | 3P | 3P | 2P | 2P | 3P | 3P | 3P | 3P | 3P | 3P | 1P | 1P | 
Resource available |  |  |  |  |  | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 

## Slide 35: New Resource Schedule Network
0 | 1 | 2
0 | 2P | 0
0 | 2 | 2
ES | ID | EF
SL | RES | SL
LS | Dur | LF
6 | 2 | 12
0 | 2P | 0
6 | 6 | 12
2 | 3 | 6
0 | 2P | 0
2 | 4 | 6
10 | 5 | 12
0 | 1P | 0
10 | 2 | 12
12 | 7 | 14
0 | 1P | 0
12 | 2 | 14
Legend
6 | 6 | 10
0 | 1P | 0
6 | 4 | 10
2 | 4 | 4
0 | 1P | 0
10 | 2 | 12

## Slide 36
TERIMA KASIH