## Slide 1
RESOURCE SCHEDULING
references:
Larson, e.w., Gray C.F., 2011, 5tH ed.;
Pinto, j.k. 2010, 2ND. ED.

## Slide 2: PROJECT CONSTRAINTS
TIME SCARCITY
RESOUCE SCARCITY

## Slide 3: Types of Resource Constraint
People
Material
Equipment

## Slide 4: Resource- Constrained Schedule Sample
0 | 1 | 2
0 | 2P | 0
0 | 2 | 2
ES | ID | EF
SL | RES | SL
LS | Dur | LF
2 | 2 | 8
2 | 2P | 2
4 | 6 | 10
2 | 3 | 6
0 | 2P | 0
2 | 4 | 6
6 | 5 | 8
2 | 1P | 2
8 | 2 | 10
10 | 7 | 12
0 | 1P | 0
10 | 2 | 12
Legend
6 | 6 | 10
0 | 1P | 0
6 | 4 | 10
2 | 4 | 4
6 | 1P | 6
8 | 2 | 10

## Slide 5: ES RESOURCE LOAD CHART
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 2P | 2 | 0 | 2 | 0 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 2P | 6 | 2 | 10 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  | 
3 | 2P | 4 | 2 | 6 | 0 |  |  | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
4 | 1P | 2 | 2 | 10 | 6 |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
5 | 1P | 2 | 6 | 10 | 2 |  |  |  |  |  |  | 1 | 1 |  |  |  |  |  |  | 
6 | 1P | 4 | 6 | 10 | 0 |  |  |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 
7 | 1P | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 
Total resource load |  |  |  |  |  | 2P | 2P | 5P | 5P | 4P | 4P | 4P | 4P | 1P | 1P | 1P | 1P |  |  | 

## Slide 6: RESOURCE CONSTRAIN SCHEDULE
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 2P | 2 | 0 | 2 | 0 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 2P | 6 | 2 | 10 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  | 
3 | 2P | 4 | 2 | 6 | 0 |  |  | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
4 | 1P | 2 | 2 | 10 | 6 |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
5 | 1P | 2 | 6 | 10 | 2 |  |  |  |  |  |  | 1 | 1 |  |  |  |  |  |  | 
6 | 1P | 4 | 6 | 10 | 0 |  |  |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 
7 | 1P | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 
Total resource load |  |  |  |  |  | 2P | 2P | 5P | 5P | 4P | 4P | 4P | 4P | 1P | 1P | 1P | 1P |  |  | 
Resource available |  |  |  |  |  | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 

## Slide 7: RESOURCE CONSTRAIN SCHEDULE
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 2P | 2 | 0 | 2 | 0 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 2P | 6 | 6 | 12 | 0 |  |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 
3 | 2P | 4 | 2 | 6 | 0 |  |  | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
4 | 1P | 2 | 2 | 10 | 6 |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
5 | 1P | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 
6 | 1P | 4 | 6 | 10 | 0 |  |  |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 
7 | 1P | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 | 
Total resource load |  |  |  |  |  | 2P | 2P | 3P | 3P | 2P | 2P | 3P | 3P | 3P | 3P | 3P | 3P | 1P | 1P | 
Resource available |  |  |  |  |  | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 

## Slide 8: New Resource Schedule Network
0 | 1 | 2
0 | 2P | 0
0 | 2 | 2
ES | ID | EF
SL | RES | SL
LS | Dur | LF
6 | 2 | 12
0 | 2P | 0
6 | 6 | 12
2 | 3 | 6
0 | 2P | 0
2 | 4 | 6
10 | 5 | 12
0 | 1P | 0
10 | 2 | 12
12 | 7 | 14
0 | 1P | 0
12 | 2 | 14
Legend
6 | 6 | 10
0 | 1P | 0
6 | 4 | 10
2 | 4 | 4
0 | 1P | 0
10 | 2 | 12

## Slide 9: Exercise 1
A. Given the network plan that follows, compute the early, late, and slack times. What is the project duration?
B. Assume only one Carpenter and two Electrician are available. Which activities are now critical? What is the project duration now?
0 | 1 | 
 | C | 
 | 3 | 
 | 2 | 
 | C | 
 | 4 | 
 | 4 | 
 | E | 
 | 3 | 
 | 6 | 
 | C | 
 | 2 | 
 | 5 | 
 | 2-E | 
 | 5 | 
 | 3 | 
 | C | 
 | 1 | 

## Slide 10: Exercise - 2
Activity | Description | Duration | Predecessor | Member Assigned
A | Assign Bids | 5 days | None | Tom
B | Document Awards | 5 days | A | Jeff
C | Calculate Costs | 5 days | A | Jeff
D | Select Winning Bid | 1 day | B, C | Sue
E | Develop PR Campaign | 4 days | D | Carol

## Slide 11: Exercise - 3
Activity | Duration | Predecessors | Number of workers per day
A | 5 | - | 6
B | 4 | A | 2
C | 5 | A | 4
D | 6 | A | 3
E | 6 | B | 3
F | 6 | C | 2
G | 4 | D | 4
H | 7 | E,F | 3
I | 5 | G | 4
J | 3 | G | 2
K | 5 | H,I,J | 5
Given the network plan that follows, compute the early, late, and slack times. What is the project duration?
Assume maximum resources available are 8 workers per week. Which activities are now critical? What is the project duration now?

## Slide 12
TERIMA KASIH