## Slide 1: Analysis Quantitative in Project Management
IS Project Management

## Slide 2: Principles of effective cost estimation
Principle 1: Divide and conquer.
  To make a better estimate, you should divide the project up into individual subsystems.
  Then divide each subsystem further into the activities that will be required to develop it.
  Next, you make a series of detailed estimates for each individual activity.
  And sum the results to arrive at the grand total estimate for the project.

## Slide 3: Principles of effective cost estimation
Principle 2: Include all activities when making estimates.
  The time required for all development activities must be taken into account.
  Including:
      Prototyping
      Design
      Inspecting
      Testing
      Debugging
      Writing user documentation
      Deployment.

## Slide 4: Principles of effective cost estimation
Principle 3: Base your estimates on past experience combined with knowledge of the current project.
  If you are developing a project that has many similarities with a past project:
    You can expect it to take a similar amount of work.
  Base your estimates on the personal judgement of your experts
    or
  Use algorithmic models developed in the software industry as a whole by analyzing a wide range of projects.
    They take into account various aspects of a project’s size and complexity, and provide formulas to compute anticipated cost.

## Slide 5: Algorithmic models
Allow you to systematically estimate development effort.
  Based on an estimate of some other factor that you can measure, or that is easier to estimate:
    The number of use cases
    The number of distinct requirements
    The number of classes in the domain model
    The number of widgets in the prototype user interface
    An estimate of the number of lines of code

## Slide 6: Algorithmic models
  A typical algorithmic model uses a formula like the following:
    COCOMO:
    Functions Points:
E = a + bNc
S = W1F1 + W2F2 +W3F3 + …
Notes: E effort
N number of requirements or use cases or lines of code
S system size
W weight
F Feature  number of inputes, tables in a database, usecases, etc

## Slide 7: Principles of effective cost estimation
Principle 4: Be sure to account for differences when extrapolating from other projects.
  Different software developers
  Different development processes and maturity levels
  Different types of customers and users
  Different schedule demands
  Different technology
  Different technical complexity of the requirements
  Different domains
  Different levels of requirement stability

## Slide 8: Principles of effective cost estimation
Principle 5: Anticipate the worst case and plan for contingencies.
  Develop the most critical use cases first
    If the project runs into difficulty, then the critical features are more likely to have been completed
  Make three estimates:
    Optimistic (O)
      Imagining a everything going perfectly
    Likely (L)
      Allowing for typical things going wrong
    Pessimistic
      Accounting for everything that could go wrong

## Slide 9: Principles of effective cost estimation
Principle 6: Combine multiple independent estimates.
  Use several different techniques and compare the results.
  If there are discrepancies, analyze your calculations to discover what factors causing the differences.
  Use the Delphi technique.
    Several individuals initially make cost estimates in private.
    They then share their estimates to discover the discrepancies.
    Each individual repeatedly adjusts his or her estimates until a consensus is reached.

## Slide 10: Principles of effective cost estimation
Principle 7: Revise and refine estimates as work progresses
  As you add detail.
  As the requirements change.
  As the risk management process uncovers problems.

## Slide 11: Building Software Engineering Teams
Software engineering is a human process.
  Choosing appropriate people for a team, and assigning roles and responsibilities to the team members, is therefore an important project management skill
  Software engineering teams can be organized in many different ways

## Slide 12: Software engineering teams
Egoless team:
  In such a team everybody is equal, and the team works together to achieve a common goal.
  Decisions are made by consensus.
  Most suited to difficult projects with many technical challenges.

## Slide 13: Software engineering teams
Hierarchical manager-subordinate structure:
  Each individual reports to a manager and is responsible for performing the tasks delegated by that manager.
  Suitable for large projects with a strict schedule where everybody is well-trained and has a well-defined role.
  However, since everybody is only responsible for their own work, problems may go unnoticed.

## Slide 14: Software engineering teams
Chief programmer team:
  Midway between egoless and hierarchical.
  The chief programmer leads and guides the project.
  He or she consults with, and relies on, individual specialists.

## Slide 15: Choosing an effective size for a team
  For a given estimated development effort, in person months, there is an optimal team size.
    Doubling the size of a team will not halve the development time.
  Subsystems and teams should be sized such that the total amount of required knowledge and exchange of information is reduced.
  For a given project or project iteration, the number of people on a team will not be constant.
  You can not generally add people if you get behind schedule, in the hope of catching up.

## Slide 16: Skills needed on a team
  Architect
  Project manager
  Configuration management and build specialist
  User interface specialist
  Technology specialist
  Hardware and third-party software specialist
  User documentation specialist
  Tester

## Slide 17: Project Scheduling and Tracking
  Scheduling is the process of deciding:
    In what sequence a set of activities will be performed.
    When they should start and be completed.
  Tracking is the process of determining how well you are sticking to the cost estimate and schedule.

## Slide 18: Some Basic Project Management Terminology
Deliverable: some concrete thing which is to be delivered, to the client or internally to the development team; e.g.
  Specifications reports
  Executable program
  Source code
Task/Activity: something we have to do during the project; e.g.
  Defining user requirements
  Coding a module
  Doing system testing
Each task or activity will take some length of time
  Referred to as duration of task
  Sometimes measured in days, weeks, etc.
  Sometimes measured in person-days, person-weeks, etc.
  Person-day = number of people X number of days
    Example: 12 person days for writing all code could mean 1 person 12 days or 4 people 3 days
    Note: not always true that a task that takes 1 programmer 12 days would take 12 programmers 1 day

## Slide 19: Dependencies and Milestones
For a given task or activity, may be impossible to start it without some other task(s) or activity(ies) having been completed; e.g.
  Cannot start coding without completing design
  Cannot start system testing without completing code integration and test plan
If task B cannot start without A being completed, we say
  B depends on A
  There is a dependency between A and B
Milestone: some achievement which must be made during the project; e.g.
  Delivering some deliverable
  Completing some task
Note, delivering a deliverable may be a milestone, but not all milestones are associated with deliverables

## Slide 20: Setting and Making Deadlines
Deadline time by which milestone has to be met
  Some deadlines are set by the client
  Others are set by us on project to make sure project stays on track
To set a deadline for completing task T, we must consider how long it will take to:
  Complete the tasks that task T depends on
  Complete task T itself
If we miss a deadline, we say (euphemistically) “the deadline has slipped”
  This is virtually inevitable
Important tasks for project managers
  Monitor whether past deadlines have slipped
  Monitor whether future deadlines are going to slip
  Allocate or reallocate resources to help make deadlines
PERT chart and Gantt charts help project managers do these things (among others)

## Slide 21: PERT Charts
PERT = Project Evaluation and Review Technique
PERT chart = graphical representation of the scheduling of events in a project
Sample PERT Chart:
A PERT chart is a graph
  Edges are tasks/activities that need to be done
  Nodes are the events or milestones
Task edge T from event node E1 to event node E2 signifies:
  Until event E1 happens, task T cannot be started
  Until task T finishes, event E2 cannot happen
Events often simply represent completion of tasks associated with arrows entering it
1
0
0
2
4
4
3
10
6
4
7
7
A
4
B
2
C
3
5
10
10
D
3
6
13
13
E
3
F
3

## Slide 22: PERT Chart Task Edges
Parts of a task/activity edge
Task letter:
  Often keyed to a legend to tell which task it represents
Task duration = how long (e.g. days, hours) task will take
D
5
Task duration
Task letter

## Slide 23: PERT Chart Event Nodes
5
9
19
Event Number:
Sequence number assigned
Only task edges indicate dependencies
Earliest Completion Time (ECT):
Earliest time this event can be achieved, given durations and dependencies
Latest Completion Time (LCT):
Latest time that this event could be safely achieved

## Slide 24: Building a PERT Chart
Make a list of all project tasks (and events if possible).
Find interrelated task dependencies (what task has to be completed before other tasks)
Draw initial PERT without durations, ECTs or LCTs
Estimate duration of each task
Fill in durations
Calculate ECTs and LCTs
We will do this for an example system:
   Generic software system with 3 modules
Steps:

## Slide 25: Example: Generic Software Project
TASK ID Task Description
A Specification
B High Level Design
C Detailed Design
D Code/Test Main module
E Code/Test DB module
F Code/Test UI module
G Write test plan
H Integrate/System Test
I Write User Manual
J Typeset User Manual
To start PERT chart: identify dependencies between tasks

## Slide 26: Dummy Tasks
Sometimes it is necessary to use dummy tasks:
  Shows the dependency between 2 events where no activity is performed
Example:
  Events 3, 4 signify the compilation of separate modules.
  Create an event 5 to signify “all modules compiled together”.
Denote dummy tasks using dash lines
3
9
10
4
9
12
5
9
12
T
3

## Slide 27: Example: Tasks with Dependencies
To start the PERT, identify the dependencies amongst tasks
TASK ID Task Description Preceed ID Succ. ID
A Specification 1 2
B High Level Design 2 3
C Detailed Design 3 4
D Code/Test Main 4 5
E Code/Test DB 4 6
F Code/Test UI 4 7
G Write test plan 4 8
Dummy Task 5 8
Dummy Task 6 8
Dummy Task 7 8
H Integrate/System Test 8 9
I Write User Manual 8 10
J Typeset User Manual 10 9

## Slide 28: Software Example: Skeleton PERT Chart
1
A
2
B
3
C
4
E
5
6
7
8
H
9
1
J
F
D
I
G
Note: dummy tasks connecting events 5, 6 and 7 to 8

## Slide 29: Estimating Durations
Suggestions for estimating durations of tasks:
  Don’t just make up a number
  Look at previous similar tasks from other projects and use those as guidelines
  Try to identify factors such as difficulty, skill level
    Each weighting factor will help you make a better estimate
Factors to consider:
  Difficulty of task
  Size of team
  Experience of team
  Number, attitude and availability of end users
  Management commitment
  Other projects in progress

## Slide 30: PERT Chart With Durations
1
A
2
B
3
C
4
E
5
6
7
8
H
9
1
J
F
D
I
G
3
2
2
7
2
3
6
2
1
5
Say we have estimated durations of all tasks (in days)
New PERT chart, with durations filled in:
Note, dummy tasks (dashed lines) always have a duration of zero
Notes: Dummy tasks always have 0 duration.
From this, we can calculate ECTs and LCTs

## Slide 31: Calculating ECTs
ECT = earliest time event can be completed
To calculate:
  For an event not depending on others: ECT = 0
    Usually this is the first event
  For an event E depending on one or more others:
    Calculate ECTs of event(s) that E depends on
    Add duration(s) of task(s) leading to E
    If E depends on more than one event, take MAX
Proceed left to right (  ) through the chart
Exercise: calculate the ECT for our example.

## Slide 32: Calculating LCT
LCT = latest time event can be completed, while still finishing last ask at indicated time
To calculate:
  For an event which no other events depend on: LCT = ECT
    Generally there will only be one such event
  For an event E which one or more others depend on:
    Calculate LCTs of event(s) that depend on E
    Subtract duration(s) of task(s) leading from E
    If more than one event depends on E, take MINIMUM
Proceed right to left (  ) through PERT chart
Exercise: calculate LCT for our example

## Slide 33: Critical Path
Red line is the critical path
What does it represent?

## Slide 34: Uses of PERT Charts
We can use PERT charts for:
  Determining the estimated time to complete a project
  Deriving actual project dates
  Allocating resources
  Identifying potential and current problems (is one task behind schedule?, can we shuffle people?)
Critical Path: Path through chart such that if any deadline slips, the final deadline slips (where all events have ECT = LCT (usually there is only one)
In software example:
  Task I is not on the critical path: even if we don’t finish it until time 18, we’re still okay
  Task D is on the critical path: if we don’t finish it until for example, time 16, then:
    We can’t start task H (duration 3) until time 16
    So we can’t complete task H until time 21
We can use PERT charts for
  Identifying the critical path
  Reallocating resources, e.g. from non-critical to critical tasks.

## Slide 35: PERT Chart Exercise
Task Prec Tasks Description Time(hrs)
A none decide on date for party 1
B A book bouncy castle 1
C A send invitations 4
D C receive replies 7
E D buy toys and balloons 1
F D buy food 3
G E blow up balloons 2
H F make food 1
I H, G decorate 1
J B get bouncy castle 1
K J, I have party 1
L K clean up 4
M K send back bouncy castle 1
N L send thank you letters 3
O M donate unwanted gifts 3

## Slide 36: Review
Create your daily activities and durations using PERT
Find out about COCOMO