## Slide 1: Process and customizations
Information System Project Management

## Slide 2: Project Management Process
Project Processes : projects are composed of process. A process is a series of actions bringing about a result.
Project processes are performed by people and generally fall into one of two major categories :
  Project Management Processes describe, organized and complete the work of the project
  Product – oriented processes
  specify and create the project’s product. Product – oriented processes are typically defined by the project life and vary by application area

## Slide 3: Project Management Process
Process Groups : Project management processes can be organized into five groups of one or more processes each :
  Initiating processes : authorizing the project phase
  Planning process : defining and refining objectives and selecting the best of the alternatives courses of action to attain the objectives that the project was undertaken to address
  Executing processes : coordinating people and other resources to carry out the plan
  Controlling processes : ensuring that monitoring and measuring progress regularly to identify variances from plan so that corrective action can be taken when necessary meet project objectives
  Closing processes : formalizing acceptance of the project or phase and bringing it to an orderly end

## Slide 4: Project Management Process
Process Interactions : within each process group, the individual processes are linked by their inputs and outputs.
So each process can describe in terms :
  Inputs : documents or documentable items that will be acted upon
  Tools and techniques : mechanism applied to the inputs to create the outputs
  Outputs : documents or documentable items that are a result of the process

## Slide 5: Project Management Process
Core processes : some planning processes have clear dependencies that require them to be performed in essentially the same order on most project.

## Slide 6: Project Management Process
Core planning processes include :
Scope planning : developing a written scope statement as the basis for future project decisions
Scope definition : subdiving the major project deliverables into smaller, more manageable components
Activity definition : identifying the specific activities that must be performed to produce the various project deliverable
Activity sequencing : identifying and documenting interactivity dependencies

## Slide 7: Project Management Process
Activity duration estimating : estimating the number of work periods that will be needed to complete individual activities
Schedule development : analyzing activity sequences, activity durations, and resource requirements to create the project schedule
Risk management planning : deciding how to approach and plan for risk management in project

## Slide 8: Project Management Process
Resource Planning : determining what resources (people, equipment, materials) and what quantities of each should be used to perform project activities
Cost Estimating : developing an approximation (estimate) of the costs of the resources required to complete project activities
cost budgeting : allocating the overall cost estimate to individual work activities
Project plan development : taking the results of other planning processes and putting them into a consistent, coherent document

## Slide 9: Project Management Process
Facilitating Processes : interactions among the other planning processes are more dependent on the nature of project

## Slide 10: Project Management Process
Facilitating processes include :
Quality planning
Organizational planning
Staff acquisition
Communications planning
Risk identification
Qualitative risk analysis
Quantitative risk analysis
Risk response planning
Procurement planning
Solicitation planning

## Slide 11: Project Management Process
Executing Processes : the executing processes include core processes and facilitating processes
Project plan execution
Quality assurance
Team development
Information distribution
Solicitation
Source selection
Contract administration

## Slide 12: Project Management Process
Controlling processes : to monitor and measured project performances and as preventive action in anticipation possible problems.

## Slide 13: Project Management Process
Closing processes components are :
Contract closeout : completion and settlement of the contract, including resolution of any open systems
Administrative closure : generating, gathering and disseminating information to formalize phase or project completion, including evaluating the project and compiling lessons learned for use in planning future projects or phases

## Slide 14: Input and output of Knowledge Areas

## Slide 15: Input and output of Knowledge Areas

## Slide 16: Input and output of Knowledge Areas

## Slide 17: Input and output of Knowledge Areas

## Slide 18: Input and output of Knowledge Areas

## Slide 19: Input and output of Knowledge Areas

## Slide 20: Input and output of Knowledge Areas

## Slide 21: Input and output of Knowledge Areas

## Slide 22: Input and output of Knowledge Areas

## Slide 23: Standards & Certification
Project Management Body of Knowledge by Project Management Institute (PMI)
PRINCE ( Projects IN Controlled Environments) by OGC

## Slide 24: Reading task
Read and make resume from a journal : “Project Management in The Information Systems and Information Technologies Industries”