## Slide 1
SCOPE MANAGEMENT
Project Management
Magister Desain
Universitas Komputer Indonesia
Source:
Larson & gray, 2014
Pinto, j.k. 2010, 2ND. ED.

## Slide 2: Project scope
is everything about a project – work content as well as expected outcomes. Project scope consist of naming all activities to be performed, the resources consumed, and the end product that result, including quality standard. Scope includes a project goals, constraints, limitations.

## Slide 3: SCOPE MANAGEMENT
is the function of controlling a project in terms of its goals and objectives through the processes of conceptual development, full definition, execution, and termination.
It’s a dream until you write it down. Then it’s goal
We can control only what we have planned

## Slide 4: Defining the project
Defining the project scope
1. Project objective
2. Deliverables
3. Milestones
4. Technical requirements
5. Limits & Exclusions
6. Reviews with customer
Establishing project priorities
Creating the breakdown structure
Integrating the WBS with the Organization
Coding the WBS

## Slide 5: Establishing project priorities

## Slide 6: Establishing project priorities
Cost
Profit Potential
Time To Market
Development Risk
Others

## Slide 7: Hierarchical breakdown of the wbs

## Slide 8: Wbs example
Level 1 
Level 2 
Level 3 

## Slide 9: Integrating wbs & obs (Example)
CONCRETE
PERF DEPT 6010
M. Manning
MASONRY
PERF DEPT 6020
T. Greams
TEST
PERF DEPT 6030
K. Neumann
CIVIL
RESP DEPT
R. Kelly
CARPENTRY
PERF DEPT 5010
R. Sites
ROOFING
PERF DEPT 5020
Y. Taylor
DRYWALL
PERF DEPT 5030
D. Smith
STRUCTURAL
RESP DEPT
P. Tate
PERF DEPT 4010
S. Johnson
HOOKUP/TIE-IN
PERF DEPT 4020
P. Ottis
ELECTICAL
RESP DEPT
J. Sims
WATER/SEWER
PERF DEPT 3010
K. Wells
GAS
PERF DEPT 3020
R. Oriely
PLUMBING
RESP DEPT
R. Lee
PROJECT OFFICE
RESP DEPT
B. Smithers
WIRING

## Slide 10: Coding the wbs for information (EXAMPLE)

## Slide 11: Coding the wbs for information (EXAMPLE)
Housing Corporation
1.1 New Home Construction
1.1.1 Concrete
1.1.1.1 Pour Foundation
1.1.1.2 Install Patio
1.1.1.3 Pour Stairway
1.1.2 Framing
1.1.2.1 Frame Exterior Walls
1.1.2.2 Frame Interior Walls
1.1.2.3 Install Roofing Trusses
1.1.3 Plumbing
1.1.3.1 Install Water Lines
1.1.3.2 Install Gas Lines
1.1.3.3 Install B/K Fixtures
1.1.4 Electrical
1.1.4.1 Install Wiring
1.1.4.2 Install Outlets/Switches
1.1.4.3 Install Fixtures
1.1.5 Interior
1.1.5.1 Install Drywall
1.1.5.2 Install Carpets
1.1.5.3 Install Painting
1.1.6 Roofing
1.1.6.1 Install Felt
1.1.6.2 Install Shingles
1.1.6.3 Install Vents