## Slide 1
Project scheduling
Precedence diagram method
Project Management
Magister Sistem Informasi
Universitas Komputer Indonesia
references:
Larson, e.w., Gray C.F., 2011, 5tH ed.;
Pinto, j.k. 2010, 2ND. ED.

## Slide 2: PRECEDENCE DIAGRAM METHOD
The Precedence Diagram Method is a tool for scheduling activities in a project plan. It is a method of constructing a project schedule network diagram that uses boxes, referred to as nodes, to represent activities and connects them with arrows that show the dependencies.
Critical Tasks, noncritical tasks, and slack time
Shows the relationship of the tasks to each other
Allows for what-if, worst-case, best-case and most likely scenario
Key elements include determining predecessors and defining attributes such as
early start date
late start date
early finish date
late finish date
Duration
WBS reference

## Slide 3: PRECEDENCE DIAGRAM METHOD
Extension of AON Network
  Allows concurrent activities to overlap
  Restraints not required to model logical relationships
  Schedule logic is easier and quicker to develop
  Easier to modify
  Better represents work flow in continuous operations

## Slide 4: Types of Task Relationship
FS – Finish to Start
Start
Finish
SS – Start to Start
FF – Finish to Finish
Start
Finish
Start
Finish
SF – Start to Finish
Start
Finish

## Slide 5: Leads & Lags
Activity Lead – Lag
  Lag = time that a following activity is delayed from the start of the previous activity
  Lead = time that an activity precedes the start or finish of the next activity

## Slide 6: Leads & Lags
Lead and Lag are used to Modify Relationships
Lead and Lag Can be used with any Relationship Type (FS, FF, SS)
Normal
Finish - Start
Finish – Start
Modified by a Lead
Finish – Start
Modified by a Lag

## Slide 7: Remodeling an Appliance
Activity |  | Duration | Predecessors
A | Conduct competitive analysis | 3 | -
B | Review field sales report | 2 | -
C | Conduct tech capabilities assessment | 5 | -
D | Identify relevant specification | 2 | A,B,C
E | Conduct telephone survey | 3 | D
F | Identify relevant specification improvements | 3 | E
G | Interface with marketing staff | 1 | F
H | Develop engineering specifications | 5 | G
I | Check and debug designs | 4 | H
J | Develop testing protocol | 3 | G
K | Identify critical performance level | 2 | J
L | Assess and modify product components | 6 | I, K
M | Conduct capabilities assessment | 12 | L
N | Identify selection criteria | 3 | M
O | Develop RFQ | 4 | M
P | Develop production master schedule | 5 | N, O
Q | Liaise with sales staff | 1 | P
R | Prepare product launch | 3 | Q

## Slide 8: QUESTION
Develop Gantt chart and create a complete activity network diagram.
Identify the critical path.

## Slide 9: EXAMPLE for EMR Project
No | Activities | Duration | Predecessor
1 | Electronic Medical Reference Project |  | 
2 | Architectural Decision | 5 days | 
3 | Specification |  | 
4 | Internal Specification | 12 days | 2
5 | External Specification | 7 days | 2
6 | Feature Specification | 10 days | 2
7 | Design Phase |  | 
8 | Voice Recognition | 10 days | 4SS+7 and 5
9 | Case | 4 days | 4 and 5FS+1
10 | Screen | 2 days | 4,5
11 | Database | 25 days | 6
12 | Microphone-soundcard | 5 days | 6 and 11FF-4
13 | Digital Devices | 7 days | 6
14 | Computer I/O | 5 days | 6
15 | Review Design | 5 days | 8,9,10,11,12,13,14

## Slide 10
TERIMA KASIH