## Slide 1: WEEK 3 Information Technology Project Management
Magister Sistem Informasi
Universitas Komputer Indonesia

## Slide 2: PROJECT SELECTION

## Slide 3: WHY PROJECT SELECTION
Survey on companies IT project: over $ 50 billion a year that are created but never used by their intended clients (Pinto, 2010:92).
Firms are literally bombarded with opportunities, but no organizations enjoys infinite resources to be able to pursue every opportunity.
Selection model permit company to save time and money while maximizing the likelihood of success.

## Slide 4: PROJECT SCREENING MODEL
Manager should consider five important issues when evaluating screening model:
1. Realism
2. Capability
3. Flexibility
4. Easy to Use
5. Cost
6. Comparability

## Slide 5: ISSUES IN PROJECT SCREENING & SELECTION
Risk – factors that reflect elements of unpredictability to the firm, including:
a. Technical Risk
b. Financial Risk
c. Safety Risk
d. Quality Risk
e. Legal Exposure
2. Commercial
a. Expected ROI
b. Payback Period
c. Potential Market Share
d. Long-term market dominance, etc.
3. Internal Operating Issues
a. Need to develop / train employees
b. Change in workforce size or composition
c. Change in physical environment, manufacturing or service operations
4. Additional Factors
a. Patent protection
b. Impact on company’s image
c. Strategic Fit

## Slide 6: APPROACHES TO PROJECTS SCREENING AND SELECTIONS
Method One: Checklist Model
Method Two: Simplified Scoring Model
Method Three: The Analytical Hierarchy Process
Method Four: Profile Models

## Slide 7: CHECK LIST MODEL

## Slide 8: CHECKLIST MODEL
Based on a list of criteria that pertain to choice of projects.
Issues in deciding among several new product development opportunities:
. Cost of development
. Potential Return on Investment
. Riskiness of new venture
. Stability of the development process
. Government or stakeholder interference
. Project durability and future market potential

## Slide 9: CHECK LIST MODEL - EXAMPLE
PROJECT | CRITERIA | PERFORMANCE ON CRITERIA HIGH MEDIUM LOW |  | 
Project Alpha | Cost Profit Potential Time To Market Development Risk | X | X | X X
Project Beta | Cost Profit Potential Time To Market Development Risk | X | X X X | 
Project Gamma | Cost Profit Potential Time To Market Development Risk | X X X |  | X
Project Delta | Cost Profit Potential Time To Market Development Risk | X | X | X X

## Slide 10: SIMPLIFIED SCORING MODEL

## Slide 11: SIMPLIFIED SCORING MODEL
In the simplified scoring model, each criterion is ranked according to its relative importance.
Example:
Criterion Importance Weight
Time to market 3
Profit Potential 2
Development Risks 2
Cost 1

## Slide 12: Example: Simple Scoring Model
Project | Criteria | (A) Importance Weight | (B) Score | X (B) Weighted Score
Project Alpha | Cost Profit Potential Time To Market Development Risk Total Score | 1 2 3 2 | 3 1 2 1 | 3 2 6 2 13
Project Beta | Cost Profit Potential Time To Market Development Risk Total Score | 1 2 3 2 | 2 2 3 2 | 2 4 9 4 19
Project Gamma | Cost Profit Potential Time To Market Development Risk Total Score | 1 2 3 2 | 3 3 1 3 | 3 6 3 6 18
Project Delta | Cost Profit Potential Time To Market Development Risk Total Score | 1 2 3 2 | 1 1 3 2 | 1 2 9 4 16

## Slide 13: ANALYTICAL HIERARCHY PROCESS

## Slide 14: Analytical Hierarchy Process
AHP was developed by Dr. Thomas Saaty to adress many of the technical and managerial problems frequently associated with decission making trough scoring models.
AHP step process:
1. Structuring the hierarchy criteria
2. Allocating weight to criteria
3. Assigning numerical values to evaluation dimmensions
4. Evaluating project proposals

## Slide 15: PROFILE MODELS

## Slide 16: Profile Models
Profile Models allow managers to plot risk/return options for various alternatives and then select project that maximizes return while staying within a certain range of minimum acceptable risk.

## Slide 17: Profile Model Example
 | Risk | Return Potential
Project Saturn | 10 | 23%
Project Mercury | 6 | 16%

## Slide 18: FINANCIAL MODELS

## Slide 19: TIME VALUE OF MONEY
Financial models are all predicated on the time value of money.
Money earned today is worth more than money we expect to earn in the future.

## Slide 20: Payback Period
Payback Period = investment/annual cash saving

## Slide 21: Payback Period Example
 | Project A Revenues Outlays |  | Project B Revenues Outlays | 
Year 0 |  | 500,000 |  | 500,000
Year 1 | 50,000 |  | 75,000 | 
Year 2 | 150,000 |  | 100,000 | 
Year 3 | 350,000 |  | 150,000 | 
Year 4 | 600,000 |  | 150,000 | 
Year 5 | 500,000 |  | 900,000 | 

## Slide 22: Net Present Value
The difference between inflows cash (after tax) and investment outflows.
NPV > 0  accepted
NPV < 0  rejected
NPV = PV – I0, or
= CF1 + CF2 + …. + CFn – I0
(1+i)1 (1+i)2 (1+i)n

## Slide 23: Net Present Value Example
Assume you are considering whether or not to invest in a project that will cost $100,000 in initial investment. Your company requires a rate of return of 10%, and you expect inflation to remain relatively constant at 4%. Future cash flow as follows:
Year 1: $ 20,000
Year 2: $ 50,000
Year 3: $ 50,000
Year 4: $ 25,000

## Slide 24: Internal Rate of Return (IRR)
CF1 + CF2 + ……. + CFn - Io = 0
(1+IRR) (1+IRR)2 (1+IRR)n
If IRR > % required return  accepted
If IRR < % required return  rejected

## Slide 25: IRR Example
Suppose that a project required an initial cash investment of $ 5,000 and was expected to generate inflows of $2,500, $2,000, $2,000 for the next three years. Assume the company rate of return 10%.
Is this project worth funding?

## Slide 26: Example
Choose which project should be funded based on pay back period, IRR & NPV, at 12% rate.
Tahun | Proyek A | Proyek B
0 | (250.000.000) | (250.000.000)
1 | 100.000.000 | 100.000.000
2 | 100.000.000 | 200.000.000
3 | 100.000.000 | 0
4 | 100.000.000 | 0

## Slide 27
TERIMA KASIH