## Slide 1: PROJECT CLOSURE (MATA KULIAH MANAJEMEN PROYEK PERANGKAT LUNAK)
SUF – MPPL 2014
Sufa’atin
Program Studi Teknik Informatika
Universitas Komputer Indonesia

## Slide 2: PENGERTIAN PROJECT CLOSURE
Project Closure merupakan akhir dari kegiatan proyek. Pada intinya tahapan penutupan proyek ini adalah memberikan laoran tentang hasil apa saja yang diperoleh dari suatu rangkaian aktivitas proyek.
Pada tahap ini harus diyakinkan bahwa semua deliverable proyek telah dipenuhi. Semua pekerjaan yang belum terselesaikan (outstanding task) harus segera dicatat dan kemudian diselesaikan.
Setelah semua pekerjaan dinyatakan selesai dalam bentuk dokumen laporan resmi, maka langkah terakhir adalah pembubaran tim proyek.

## Slide 3: Mekanisme Project Closure
Manajer proyek melakukan serah terima hasil pekerjaan berupa:
  Laporan pelaksanaan pekerjaan
  Laporan penyelesaian pekerjaan
  Berita acara penyelesaian pekerjaan
  Berita acara serah terima pekerjaan
Pembubaran tim proyek

## Slide 4: Project Termination in IT Industry
40% of IT application development projects are canceled before completion.
33% of the remaining projects face significant cost and/or schedule overruns or changes in scope.
(Standish Group of Dennis, Massachusetts, 2001)

## Slide 5: Software Project Research
31% canceled before completed
53% cost 189% of their original estimates
16% complete on time and on budget
(Study by Standish Group 2001 & 2009. Survey conducted on 365 IT executive project manager with 8380 projects.)

## Slide 6: The 10 Signs of Pending IT Project Failure
Project manager don’t understand user needs.
Scope is ill defined.
Project changes are poorly managed.
Chosen technology changes.
Business needs change.
Deadlines are unrealistic.
Users are resistant.
Sponsorship is lost.
Project lack people with appropriate skills.
Best practice and lessons learned are ignored.

## Slide 7: Project Success Criteria
Success Criteria |  | Points
1 | User involvement | 19
2 | Executive management support | 16
3 | Clear statement of requirement | 15
4 | Proper planning | 11
5 | Realistic expectations | 10
6 | Smaller project milestone | 9
7 | Competent staff | 8
8 | Project team ownership | 6
9 | Clear vision and objectives | 3
10 | Hard-working, focused staff | 3
Total |  | 100

## Slide 8: Project Closure
Wrapping up the project
Performance evaluation
Retrospectives.

## Slide 9: Wrap-up Closure Checklist
 | Task | Completed? Yes/No
 | Team | 
1 | Has a schedule for reducing project staff been developed and accepted? | 
2 | Has staff been released or notified of new assignment? | 
3 | Have performance reviews for team members been conducted? | 
4 | Has staff been offered outpalcement services and career councelling activities? | 
 | Vendors/contractors | 
5 | Have performance reviews for all vendors been conducted? | 
6 | Have project accounts been finalized and billing closed? | 
 | Customer/Users | 
7 | Has the customer signed-off on the delivered product? | 
8 | Has an in-depth project review and evaluation interview with customer been conducted? | 
9 | Have users , project team, vendors, training, support, maintenance are satisfy? | 
 | Equipment and facilities | 
10 | Have project resources been transferred to other project? | 
11 | Have rental or lease equipment agreements been closed out? | 

## Slide 10: Sample Team Evaluation and Feedback Survey
 |  | Disagree Agree |  |  |  | 
Using the case below, asses each statement |  |  |  |  |  | 
1 | The team shared a sense of common purpose, and each member was willing to work toward achieving project objectives | 1 | 2 | 3 | 4 | 5
2 | Respect was shown for other points of view. Differences of opinion were encouraged and freely expressed | 1 | 2 | 3 | 4 | 5
3 | All interaction among team members occured in a comfortable, supportive atmosphere | 1 | 2 | 3 | 4 | 5

## Slide 11: FINAL PROJECT (Laporan Yang Harus Dikumpulkan)
Pendahuluan: latar belakang proyek, tujuan proyek, batasan proyek,
Struktur organisasi proyek (beserta penjelasan)
WBS
Laporan aktivitas proyek (jadwal dan resources)
Diagram network
  5.1 Waktu
  5.2 Resources
Laporan biaya proyek
Laporan Sumber Daya Manusia Proyek
Laporan risiko proyek dan mitigasi risiko
Laporan hasil kerja

## Slide 12: FINAL PROJECT (Laporan Yang Harus Dikumpulkan)(2)
10. Kesimpulan
- menyatakan keberhasilan proyek :
sesuai dengan scope, on time, dan on budget
deliverables memiliki kualitas sesuai kebutuhan
memastikan bahwa tujuan proyek berhasil dan tercapai
- menyatakan kegagalan proyek:
penyebab kegagalan
menjelaskan scope, time, atau budget yang tidak tercapai

## Slide 13: Contoh Laporan Resiko Proyek
Hasil perhitungan
Tabel risiko
No | Risk Name | Impact |  |  | Probability |  | 
 |  | High | Medium | Low | High | Medium | Low
R1 | Dokumen/arsip digital tidak dapat diakses |  | V |  | V |  | 
R2 | Proyek ini memiliki risiko terhadap kerusakan media penyimpanan | V |  |  |  | V | 
 | ... dst |  |  |  |  |  | 

## Slide 14
    TERIMA KASIH