## Slide 1
RESOURCE SCHEDULING
references:
Larson, e.w., Gray C.F., 2011, 5tH ed.;
Pinto, j.k. 2010, 2ND. ED.

## Slide 2: PROJECT CONSTRAINTS
TIME SCARCITY
RESOUCE SCARCITY

## Slide 3: Types of Resource Constraint
People
Material
Equipment

## Slide 4: Resource- Constrained Schedule Sample
 | 1 | 
 | 2P | 
 | 2 | 
ES | ID | EF
SL | RES | SL
LS | Dur | LF
 | 2 | 
 | 2P | 
 | 6 | 
 | 3 | 
 | 2P | 
 | 4 | 
 | 5 | 
 | 1P | 
 | 2 | 
 | 7 | 
 | 1P | 
 | 2 | 
Legend
 | 6 | 
 | 1P | 
 | 4 | 
 | 4 | 
 | 1P | 
 | 2 | 

## Slide 5: Resource- Constrained Schedule Sample
0 | 1 | 2
0 | 2P | 0
0 | 2 | 2
ES | ID | EF
SL | RES | SL
LS | Dur | LF
2 | 2 | 8
2 | 2P | 2
4 | 6 | 10
2 | 3 | 6
0 | 2P | 0
2 | 4 | 6
6 | 5 | 8
2 | 1P | 2
8 | 2 | 10
10 | 7 | 12
0 | 1P | 0
10 | 2 | 12
Legend
6 | 6 | 10
0 | 1P | 0
6 | 4 | 10
2 | 4 | 4
6 | 1P | 6
8 | 2 | 10

## Slide 6: ES RESOURCE LOAD CHART
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 2P | 2 | 0 | 2 | 0 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 2P | 6 | 2 | 10 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  | 
3 | 2P | 4 | 2 | 6 | 0 |  |  | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
4 | 1P | 2 | 2 | 10 | 6 |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
5 | 1P | 2 | 6 | 10 | 2 |  |  |  |  |  |  | 1 | 1 |  |  |  |  |  |  | 
6 | 1P | 4 | 6 | 10 | 0 |  |  |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 
7 | 1P | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 
Total resource load |  |  |  |  |  | 2P | 2P | 5P | 5P | 4P | 4P | 4P | 4P | 1P | 1P | 1P | 1P |  |  | 

## Slide 7: RESOURCE CONSTRAINT SCHEDULE
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 2P | 2 | 0 | 2 | 0 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 2P | 6 | 2 | 10 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  | 
3 | 2P | 4 | 2 | 6 | 0 |  |  | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
4 | 1P | 2 | 2 | 10 | 6 |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
5 | 1P | 2 | 6 | 10 | 2 |  |  |  |  |  |  | 1 | 1 |  |  |  |  |  |  | 
6 | 1P | 4 | 6 | 10 | 0 |  |  |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 
7 | 1P | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 
Total resource load |  |  |  |  |  | 2P | 2P | 5P | 5P | 4P | 4P | 4P | 4P | 1P | 1P | 1P | 1P |  |  | 
Resource available |  |  |  |  |  | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 

## Slide 8: RESOURCE CONSTRAINT SCHEDULE
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 2P | 2 | 0 | 2 | 0 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 2P | 6 | 6 | 12 | 0 |  |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 
3 | 2P | 4 | 2 | 6 | 0 |  |  | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
4 | 1P | 2 | 2 | 10 | 6 |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
5 | 1P | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 
6 | 1P | 4 | 6 | 10 | 0 |  |  |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 
7 | 1P | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 | 
Total resource load |  |  |  |  |  | 2P | 2P | 3P | 3P | 2P | 2P | 3P | 3P | 3P | 3P | 3P | 3P | 1P | 1P | 
Resource available |  |  |  |  |  | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 

## Slide 9: New Resource Schedule Network
0 | 1 | 2
0 | 2P | 0
0 | 2 | 2
ES | ID | EF
SL | RES | SL
LS | Dur | LF
6 | 2 | 12
0 | 2P | 0
6 | 6 | 12
2 | 3 | 6
0 | 2P | 0
2 | 4 | 6
10 | 5 | 12
0 | 1P | 0
10 | 2 | 12
12 | 7 | 14
0 | 1P | 0
12 | 2 | 14
Legend
6 | 6 | 10
0 | 1P | 0
6 | 4 | 10
2 | 4 | 4
0 | 1P | 0
10 | 2 | 12

## Slide 10: Exercise 1
A. Given the network plan that follows, compute the early, late, and slack times. What is the project duration?
B. Assume only one Interior Designer and two Visual Designer are available. Which activities are now critical? What is the project duration now?
0 | 1 | 
 | ID | 
 | 3 | 
 | 2 | 
 | ID | 
 | 4 | 
 | 4 | 
 | VD | 
 | 3 | 
 | 6 | 
 | ID | 
 | 2 | 
 | 5 | 
 | 2-VD | 
 | 5 | 
 | 3 | 
 | ID | 
 | 1 | 

## Slide 11: Exercise - 2
Activity | Description | Duration | Predecessor | Member Assigned
A | Assign Bids | 5 days | None | Tom
B | Document Awards | 5 days | A | Jeff
C | Calculate Costs | 5 days | A | Jeff
D | Select Winning Bid | 1 day | B, C | Sue
E | Develop PR Campaign | 4 days | D | Carol

## Slide 12: Exercise - 3
Activity | Duration | Predecessors | Number of workers per day
A | 5 | - | 6
B | 4 | A | 2
C | 5 | A | 4
D | 6 | A | 3
E | 6 | B | 3
F | 6 | C | 2
G | 4 | D | 4
H | 7 | E,F | 3
I | 5 | G | 4
J | 3 | G | 2
K | 5 | H,I,J | 5
Given the network plan that follows, compute the early, late, and slack times. What is the project duration?
Assume maximum resources available are 8 workers per day. Which activities are now critical? What is the project duration now?

## Slide 13
TERIMA KASIH